## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Executive Summary
| Table 1-1 | Executive Summary - Table 1-1
Gantt Chart - Analysis Phase - Example
| Table 1-1 | Gantt Chart - Analysis Phase -
RACI - Analysis Phase
| Table 1 | RACI - Analysis Phase
Sheet 1
| “All Drawings from the Sheet” | Sheet 1

## Executive Summary - Table 1-1
Project Title: | New Hire Onboarding Process Optimization
Problem Statement
Problem Statement | Currently, there is no established stucture or standardization of an Account Managers/Digital Sales Representatives onboarding process to serve the various countries/regions across the enterprise. A New Hire onboarding process is instrumental in welcoming our new sales colleagues to our organization and preparing them to be proficient in their roles. The New Hires onboarding process is instrumental in welcoming our new sales colleagues to our organization and preparing them to be proficient in their roles. The current state of new hire training, unfortunately, consists of variable, inconsistant, adhoc training courses that have been pieced together to be used across the enterprise. As a result Thermo Fisher, CMD and the new hires are being negatively impacted.
Impacts | * Increased ramp up times * Decreased time to proficiency * Increased time invested by Sales Managers and other organizational resources * Unstructured training leaves training up to chance. This training type can overlook key knowledge critical to on the job performance * Increased cost of training * Just in case training is inefficient. It inhibits the learner focusing on what is needG * Marketing Centric Training * No future role/career growth as a result of adhoc training
Scope & Process Boundaries
Business | CMD Global Sales
Geography/Location | North America and EMEA - Phase I
Specific processes | New Hire Training and Onboarding Process
Includes | Account Managers and Digital Sales Representatives
Excludes | Applications Team, Service IES, Channel Managers, Distributors, WIAS Team, Technical Sales Team,
Goals & Benefits
Goals | The Global Sales Training Team's goal is to build a standardize, structured and sustainable new hire onboarding program by Q1 2023. New Onboarding process is calculated to reduce ramp up time of new hires following implementation by 2 weeks providing a 1.1M productivity gain vs 2022. Establish process guideline and governance for ownership and continuing improvement prior to Q1 2023 implementation (Chromatography and Mass Spectrometry Division Global Sales Training Standard Operating Procedures (MD GST SOP) .
Benefits | * Reduced ramp up times * Increased time to proficiency * Reduced time invested by Sales Managers and other organizational resources * Standardized Training Procedures provide consistent content (curriculum approach and guiding principles) and delivery methods (training length, elearning, virtual instructor led training, instructor led training). *Reduced cost of training * Just in time training allows the new hire to fully focus on understanding and skills necessary to perform their role. * Customer/Sales Rep Centric Training * Provides future role and organizational career growth
Critical to Quality (CTQ)s / Key Metrics
CTQ | Metric |  | Baseline | Goal | Results
Timeliness | Content Development |  | Due by 12/31/22 | To have content for Tools & Systems, Business Processes, Selling Skills, Markets and Products developed by 12/31/22 | Completed
Productivity | Ramp up productivity (dollars per week) |  | 1.1M | 1.1M | 1.7M
Adoption | Number of New Hires completing the New Process |  | 10 | Avg 20 | 36
Sustainability | Number of Ambassadors ready to support |  | No Ambassador Program | 1 Per Manager | Ambassador role out Q2
Project Team & Stakeholders
Executive Sponsor | TB
Project Leader | Kimberly Hammontree
Project Team |  |  |  | Stakeholders
Name |  | Function |  | Name | Function
MB, AK |  | Sales Director/Sales Manager (2) |  | TB | Commercial Ops
ML,TB |  | Sales Operation |  | BM | Vice President, Global Sales
CF, HT |  | Account Managers (2) |  | PS | VP, EMEA Sales
MN, DW |  | Applications |  | AC | VP, Amer Sales
JT, BW |  | Ambassadors |  | AG | VP, Applications
Not Started |  | Sr. Sales Representatives |  | SG | VP, Global Marketing
TJ, LG |  | CME's
SB, CA |  | TSS's (2)
TC, MT |  | BU Marketing Leads (2)
KK, SG,RM, RR, MP |  | SAB (5)
RS, YD, HS, CR, GM, HT, SB |  | SAC (7)
SS, BR |  | HR
Project Review Plan |  |  |  | Executive Summary
Meeting Title |  | Responsible | When | Top 3 Actions Completed (since last review)
Set up Kick off meeting with sales directors and managers |  | Kimberly | Before Nov 1, 2022
Set up Kick off meeting with marketing teams |  | Kimberly | Before Nov 1, 2022
Project Team Meeting |  | Kimberly & PA | Weekly
Project Review Meeting |  | Kimberly & PA | BiWeekly
Stakeholders Project Review |  | Kimberly | Every 6 weeks
Note on B2: Author: Problem Statement: Currently, … The problem statement contains a brief description of what is the "pain" being experienced. You need to relate the problem statement to the VOC and collect quantifiable data. Additionally, indentify where it is occuring, when it is occuring, why it is occuring, etc. Specific problem including baseline with no implied solutions Good problem statements should detail the metric that represents the problem. Concise, specific, one problem only, measurable and no implied solution. See pages 80-85, 115-120 in your Training book for these next few sections. Impact - This statement describes the impact of what the problem results in. How is the problem negatively affecting the business?
Note on B13: Author: Scope: Process boundaries are necessary to keep the team on track relative to the scope of the event, communicate to the organization where you will and will not be working, and align expectations of the team. It is important to identify what the boundaries include, and exclude. Where does the process start and where does it end?
Note on B20: Author: Goal Statements: What outcome do I want? Visualize the desired results. Using the data, set a measurable and realistic goal. Goal format: Action verb + object of the action + from "current state" + to "future state" by "date". Quantitative goals should have "from x to y by z" format. e.g. Decrease average manufacturing lead time for product X from 10 days to 2 days by 31 January 2023" Draft the outline project plan by when the project will be finished Allocate time lines & responsibilities (e.g. summary Gantt chart) Develop draft financial gains and get finance approval (if appropriate) Detail quantitative (preferably) goals/targets that will measure success of the event. These are the key goals/targets that may appear replicated below in the metric tracking. (Problem Statement ties to Goals ties to Output metric) NOTE: for 8 step projects you would only define one goal that reflects our problem statement. One problem, one goal, one output metric.

## Gantt Chart - Analysis Phase -
Sample phase title block | Onboarding & Training
| Thermo Fisher CMD | Project Start: |  | 2022-03-28
| Kimberly Hammontree | Display Week: |  | 9 |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25 |  |  |  |  | 2022-05-02 |  |  |  |  | 2022-05-09 |  |  |  |  | 2022-05-16 |  |  |  |  | 2022-05-23 |  |  |  |  | 2022-05-30 |  |  |  |  | 2022-06-06 |  |  |  |  | 2022-06-13 |  |  |  |  | 2022-06-20 |  |  |  |  | 2022-06-27 |  |  |  |  | 2022-07-04 |  |  |  |  | 2022-07-11 |  |  |  |  | 2022-07-18 |  |  |  |  | 2022-07-25 |  |  |  |  | 2022-08-01 |  |  |  |  | 2022-08-08 |  |  |  |  | 2022-08-15 |  |  |  |  | 2022-08-22 |  |  |  |  | 2022-08-29 |  |  |  |  | 2022-09-05 |  |  |  |  | 2022-09-12 |  |  |  |  | 2022-09-19 |  |  |  |  | 2022-09-26 |  |  |  |  | 2022-10-03 |  |  |  |  | 2022-10-10 |  |  |  |  | 2022-10-17 |  |  |  |  | 2022-10-24 |  |  |  |  | 2022-10-31 |  |  |  |  | 2022-11-07 |  |  |  |  | 2022-11-14 |  |  |  |  | 2022-11-21 |  |  |  |  | 2022-11-28 |  |  |  |  | 2022-12-05 |  |  |  |  | 2022-12-12 |  |  |  |  | 2022-12-19 |  |  |  |  | 2022-12-26 |  |  |  |  | 2023-01-02
| ANALYSIS PHASE | [6 empty] | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6
| TASK: Analysis | ASSIGNED TO | PROGRESS | START | END | DUE DATE | DAYS | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Executive Summary | bar: 2022-05-23 27 F
| Define the problem/s | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Define the business impact | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Define the project scope & process boundaries | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Business | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Geography/Location | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Specific Process | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Audience Inclusion | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Audience Exclusion | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Define our goals and objectives | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Define the impacts as a result of our goals | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Define the Critical to Quality (CTC’s) and Key Metrics | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Timeliness | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Productivity | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Adoption | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Sustainability | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Identify the project team and stakeholders | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Project Team | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Stakeholders | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Map project review Plan | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
PRESENT EXECUTIVE SUMMARY | bar: 2022-04-11 12 T; 2022-05-23 27 F
| REVIEW | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | bar: 2022-05-23 27 F
| eLearning Content Review | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Completion Rates Review | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| SURVEYS |  | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | bar: 2022-05-23 27 F
| Regional Manager Surveys | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Survey New Hires that recently completed the program | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
FINALIZE TOPICS | bar: 2022-05-23 27 F
| Markets | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Products | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Tools & Systems | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Business Processes | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Selling Skills | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Ambassador Role | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| Certification Criteria | KIMBERLY HAMMONTREE | 100% | 2022-03-28 | 2022-05-27 | 2022-05-27 | DAYS: 43
| DESIGN PHASE | Design Phase Start: |  | 2022-05-30 |  |  | 2022-03-28 28 M: 2022-03-28; 2022-04-04 4 M: 2022-04-04; 2022-04-11 11 M: 2022-04-11; 2022-04-18 18 M: 2022-04-18; 2022-04-25 25 M: 2022-04-25; 2022-05-02 2 M: 2022-05-02; 2022-05-09 9 M: 2022-05-09; 2022-05-16 16 M: 2022-05-16; 2022-05-23 23 M: 2022-05-23; 2022-05-30 30 M: 2022-05-30; 2022-06-06 6 M: 2022-06-06; 2022-06-13 13 M: 2022-06-13; 2022-06-20 20 M: 2022-06-20; 2022-06-27 27 M: 2022-06-27; 2022-07-04 4 M: 2022-07-04; 2022-07-11 11 M: 2022-07-11; 2022-07-18 18 M: 2022-07-18; 2022-07-25 25 M: 2022-07-25; 2022-08-01 1 M: 2022-08-01; 2022-08-08 8 M: 2022-08-08; 2022-08-15 15 M: 2022-08-15; 2022-08-22 22 M: 2022-08-22; 2022-08-29 29 M: 2022-08-29; 2022-09-05 5 M: 2022-09-05; 2022-09-12 12 M: 2022-09-12; 2022-09-19 19 M: 2022-09-19; 2022-09-26 26 M: 2022-09-26; 2022-10-03 3 M: 2022-10-03; 2022-10-10 10 M: 2022-10-10; 2022-10-17 17 M: 2022-10-17; 2022-10-24 24 M: 2022-10-24; 2022-10-31 31 M: 2022-10-31; 2022-11-07 7 M: 2022-11-07; 2022-11-14 14 M: 2022-11-14; 2022-11-21 21 M: 2022-11-21; 2022-11-28 28 M: 2022-11-28; 2022-12-05 5 M: 2022-12-05; 2022-12-12 12 M: 2022-12-12; 2022-12-19 19 M: 2022-12-19; 2022-12-26 26 M: 2022-12-26; 2023-01-02 2 M: 2023-01-02
|  | Display Week: |  | 11 |  |  |  | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6
| TASK: Content Design | ASSIGNED TO | PROGRESS | START | END | DUE DATE | DAYS | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| MARKETS & APPLICATIONS | GST & SAC Team |  |  |  |  | DAYS: 61
| CLINICAL | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| ENVIRONMENTAL & GEOLOGICAL | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| FOOD & AGRICULTURE | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| INDUSTRIAL | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| PAHRMA & BIOTECH | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| OMICS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| PRODUCTS | GST & SAC Team |  |  |  |  | DAYS: 61
| CCS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
Sample phase title block | CDS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| DIA | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| GC-GCMS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| HPLC | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| IC/SP | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| IOMS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| LSMS | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| TEA | KIMBERLY HAMMONTREE & SAC Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| TOOLS & SYSTEMS | GST & SAB Team |  |  |  |  | DAYS: 61
| SFDC | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| CPQ | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| CPQ - Quoting Service | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| HIGHSPOT | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| BRAINSHARK | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| BUSINESS PROCESSES | GST & SAB Team |  |  |  |  | DAYS: 61
| ECOMMERCE | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| FIANCIAL SERVICES | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| APPLICATIONS TEAM | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| ORDER MANAGEMENT | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| ESCALATIONS | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| IES | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
SELLING SKILLS
Sample phase title block | SANDLER | NG | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| AMBASSADOR ROLE | GST & SAB Team | bar: DAYS
| SELECTION CRITERIA | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | bar: DAYS
| ROLE | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | bar: DAYS
| RESPONSIBILITIES | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | bar: DAYS
| ON-THE-JOB (OTJ)/COACHING ACTIVITIES | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | bar: DAYS
| PROGRESSION CHECKLIST | KIMBERLY HAMMONTREE & SAB Team | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | bar: DAYS
| ASSESSMENTS & CERTIFICATIONS | KIMBERLY HAMMONTREE
| WHO IS THE AUDIENCE | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| WHAT TYPES OF ASSESSMENT WILL BE USED | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| WHEN WILL THE ASSESSMENT OCCUR | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| WHAT ARE THE ASSESSMENT CERTIFICATIONS REQUIREMENTS | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| WHY ARE THE ASSESSMENTS AND CERTICATION NEEDED | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| HOW WILL THE ASSESSMENT BE ADMINISTERED AND CERTIFICATE GIVEN | KIMBERLY HAMMONTREE | 100% | 2022-05-30 | 2022-08-26 | 2022-08-26 | DAYS: 61
| DEVELOPMENT PHASE | Project Start: |  | 1/2/2023 - 3/17/2023 |  |  | 2022-03-28 28 M: 2023-01-02; 2022-04-04 4 M: 2023-01-09; 2022-04-11 11 M: 2023-01-16; 2022-04-18 18 M: 2023-01-23; 2022-04-25 25 M: 2023-01-30; 2022-05-02 2 M: 2023-02-06; 2022-05-09 9 M: 2023-02-13; 2022-05-16 16 M: 2023-02-20; 2022-05-23 23 M: 2023-02-27; 2022-05-30 30 M: 2023-03-06; 2022-06-06 6 M: 2023-03-13; 2022-06-13 13 M: 2023-03-20; 2022-06-20 20 M: 2023-03-27; 2022-06-27 27 M: 2023-04-03; 2022-07-04 4 M: 2023-04-10; 2022-07-11 11 M: 2023-04-17; 2022-07-18 18 M: 2023-04-24; 2022-07-25 25 M: 2023-05-01; 2022-08-01 1 M: 2023-05-08; 2022-08-08 8 M: 2023-05-15
|  | Display Week: |  | 11 |  |  | 2022-03-28 28 M: 1900-01-03; 2022-03-28 29 T: 1900-01-04; 2022-03-28 30 W: 1900-01-05; 2022-03-28 31 TH: 1900-01-06; 2022-03-28 1 F: 1900-01-07; 2022-04-04 5 T: 1; 2022-04-04 6 W: 2; 2022-04-04 7 TH: 3; 2022-04-04 8 F: 4; 2022-04-11 12 T: 1; 2022-04-11 13 W: 2; 2022-04-11 14 TH: 3; 2022-04-11 15 F: 4; 2022-04-18 19 T: 1; 2022-04-18 20 W: 2; 2022-04-18 21 TH: 3; 2022-04-18 22 F: 4; 2022-04-25 26 T: 1; 2022-04-25 27 W: 2; 2022-04-25 28 TH: 3; 2022-04-25 29 F: 4; 2022-05-02 3 T: 1; 2022-05-02 4 W: 2; 2022-05-02 5 TH: 3; 2022-05-02 6 F: 4; 2022-05-09 10 T: 1; 2022-05-09 11 W: 2; 2022-05-09 12 TH: 3; 2022-05-09 13 F: 4; 2022-05-16 17 T: 1; 2022-05-16 18 W: 2; 2022-05-16 19 TH: 3; 2022-05-16 20 F: 4; 2022-05-23 24 T: 1; 2022-05-23 25 W: 2; 2022-05-23 26 TH: 3; 2022-05-23 27 F: 4; 2022-05-30 1 T: 1; 2022-05-30 2 W: 2; 2022-05-30 3 TH: 3; 2022-05-30 4 F: 4; 2022-06-06 7 T: 1; 2022-06-06 8 W: 2; 2022-06-06 9 TH: 3; 2022-06-06 10 F: 4; 2022-06-13 14 T: 1; 2022-06-13 15 W: 2; 2022-06-13 16 TH: 3; 2022-06-13 17 F: 4; 2022-06-20 21 T: 1; 2022-06-20 22 W: 2; 2022-06-20 23 TH: 3; 2022-06-20 24 F: 4; 2022-06-27 28 T: 1; 2022-06-27 29 W: 2; 2022-06-27 30 TH: 3; 2022-06-27 1 F: 4
| TASK: Content Development | ASSIGNED TO | PROGRESS | START | END | DUE DATE | DAYS | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| MARKETS & APPLICATIONS | MARKETS TEAM | DUE Q3
| CLINICAL | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| ENVIRONMENTAL & GEOLOGICAL | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| FOOD & AGRICULTURE | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| INDUSTRIAL | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
Sample phase title block | PAHRMA & BIOTECH | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| OMICS | MARKET MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| PRODUCTS | PRODUCT MANAGEMENT TEAM
| CCS | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| CDS | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| DIA | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| GC-GCMS | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| HPLC | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| IC/SP | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| IOMS | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| LSMS | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| TEA | PRODUCT MANAGER & KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| TOOLS & SYSTEMS | GST Team
| SFDC | AH | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| CPQ | MM | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| CPQ - Quoting Service | MM | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| HIGHSPOT | JH | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| BRAINSHARK | PA | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| BUSINESS PROCESSES | GST TEAM
| ECOMMERCE | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| FIANCIAL SERVICES | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| APPLICATIONS TEAM | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| ORDER MANAGEMENT | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
Sample phase title block | ESCALATIONS | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| IES | SAC Team | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| SALES SYSTEMS | GST TEAM
| ACCOUNT MANAGEMENT | ME | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| SANDLER | NG | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| AMBASSADOR ROLE | GST TEAM
| SELECTION CRITERIA | REGIONAL MANAGERS/HR/KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| ROLE | REGIONAL MANAGERS/HR/KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| RESPONSIBILITIES | REGIONAL MANAGERS/HR/KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| ON-THE-JOB (OTJ)/COACHING ACTIVITIES | REGIONAL MANAGERS/HR/KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| PROGRESSION CHECKLIST | REGIONAL MANAGERS/HR/KIMBERLY | 0% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| ASSESSMENTS & CERTIFICATIONS | KIMBERLY HAMMONTREE
| WHO IS THE AUDIENCE | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| WHAT TYPES OF ASSESSMENT WILL BE USED | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| WHEN WILL THE ASSESSMENT OCCUR | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| WHAT ARE THE ASSESSMENT CERTIFICATIONS REQUIREMENTS | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| WHY ARE THE ASSESSMENTS AND CERTICATION NEEDED | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| HOW WILL THE ASSESSMENT BE ADMINISTERED AND CERTIFICATE GIVEN | KIMBERLY HAMMONTREE | 100% | 2022-08-29 | 2022-12-02 | 2022-12-02 | DAYS: 64
| IMPLEMENTATION PHASE | Project Start: |  | 2022-12-05 |  |  | M: 2023-03-20; M: 2023-03-27; M: 2023-04-03
|  | Display Week: |  | 2 |  |  | M: 1900-01-21; T: 1900-01-22; W: 1900-01-23; TH: 1900-01-24; F: 1900-01-25; T: 1; W: 2; TH: 3; F: 4; T: 1; W: 2; TH: 3; F: 4
| TASK: Implementation Phase | ASSIGNED TO | PROGRESS | START | END | DUE DATE | DAYS | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| MARKETS & APPLICATIONS | GST TEAM |  |  |  |  | M: GO LIVE
Sample phase title block | CLINICAL | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ENVIRONMENTAL & GEOLOGICAL | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| FOOD & AGRICULTURE | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| INDUSTRIAL | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| PAHRMA & BIOTECH | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| OMICS | MARKETS MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| PRODUCTS | GST TEAM
| CCS | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| CDS | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| DIA | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| GC-GCMS | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| HPLC | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| IC/SP | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| IOMS | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| LSMS | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| TEA | PRODUCT MANAGER | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| TOOLS & SYSTEMS | SAC Team
| SFDC | AH | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| CPQ | MM | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| CPQ - Quoting Service | MM | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| HIGHSPOT | JH | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| BRAINSHARK | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| BUSINESS PROCESSES | SAC Team
Sample phase title block | ECOMMERCE | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| FIANCIAL SERVICES | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| APPLICATIONS TEAM | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ORDER MANAGEMENT | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ESCALATIONS | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| IES | PA | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| SALES SYSTEMS | GST TEAM
| ACCOUNT MANAGEMENT | ME | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| SANDLER | NG | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| AMBASSADOR ROLE | GST TEAM
| SELECTION CRITERIA | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ROLE | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| RESPONSIBILITIES | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ON-THE-JOB (OTJ)/COACHING ACTIVITIES | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| PROGRESSION CHECKLIST | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| ASSESSMENTS & CERTIFICATIONS | GST TEAM
| WHO IS THE AUDIENCE | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| WHAT TYPES OF ASSESSMENT WILL BE USED | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| WHEN WILL THE ASSESSMENT OCCUR | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| WHAT ARE THE ASSESSMENT CERTIFICATIONS REQUIREMENTS | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| WHY ARE THE ASSESSMENTS AND CERTICATION NEEDED | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| HOW WILL THE ASSESSMENT BE ADMINISTERED AND CERTIFICATE GIVEN | KIMBERLY HAMMONTREE | 100% | 2022-12-05 | 2022-12-16 | 2022-12-16 | DAYS: 10
| EVALUATION PHASE | Project Start: |  | 2023-01-02 |  |  | M: 2023-03-20; M: 2023-03-27; M: 2023-04-03
|  | Display Week: |  | 2 |  |  |  | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 |  | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4
| TASK: Evaluation Phase | ASSIGNED TO | PROGRESS | START | END | DUE DATE | DAYS | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| MARKETS & APPLICATIONS | GST Team |  |  |  |  | M: GO LIVE
| CLINICAL | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| ENVIRONMENTAL & GEOLOGICAL | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| FOOD & AGRICULTURE | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| INDUSTRIAL | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| PHARMA & BIOTECH | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| OMICS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-01-02 | 2023-04-28 | DAYS: 80
| PRODUCTS | GST Team
| CCS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| CDS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| DIA | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| GC-GCMS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| HPLC | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| IC/SP | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| IOMS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| LSMS | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| TEA | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| TOOLS & SYSTEMS | SAC Team
| SFDC | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| CPQ | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
Sample phase title block | CPQ - Quoting Service | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| HIGHSPOT | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| BRAINSHARK | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| BUSINESS PROCESSES | GST TEAM
Sample phase title block | ECOMMERCE | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| FIANCIAL SERVICES | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| APPLICATIONS TEAM | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| ORDER MANAGEMENT | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| ESCALATIONS | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| IES | PA | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| SALES SYSTEMS | GST TEAM
| ACCOUNT MANAGEMENT | ME | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| SANDLER | NG | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | DAYS: 80
| AMBASSADOR ROLE | GST TEAM
| SELECTION CRITERIA | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | bar: DAYS
| ROLE | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | bar: DAYS
| RESPONSIBILITIES | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | bar: DAYS
| ON-THE-JOB (OTJ)/COACHING ACTIVITIES | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | bar: DAYS
| PROGRESSION CHECKLIST | KIMBERLY HAMMONTREE | 100% | 2023-01-02 | 2023-04-30 | 2023-04-30 | bar: DAYS

## RACI - Analysis Phase
D | Assists those who are responsible for a task.
R | Assigned to complete the task or deliverable.
A | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Provides support during implementation.
C | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Must be informed after a decision or action.
Revison # | RACI FOR THE ANALYSIS STAGE Project Manager: Kimberly Hammontree | ROLES | Sales Ops | Leadership Team | GST Team | Sales Managers | Sr. Account Manager | TSS/SME'S | HR Team | Marketing Team | Product Management Team | SAC Team | SAB Team | ML | TB | BM | KH | ME | NG | PA | MB | RL | MN | DW | RS | BF | TC
1 |  | Status | Departments Involved | [10 empty] | Sales Operations |  |  | GST Team |  |  |  | Sales Manager |  | TSS/SME's |  | HR Team |  | Marketing Team | Project Management Team
PHASE 1 - ANALYSIS
EXECUTIVE SUMMARY
DEFINE
| Define the problem/s | Completed | A | I | R | [8 empty] | A | I | I | R
| Define the business impact | Completed | A | I | R | [8 empty] | A | I | I | R
| Define the Project Scope & Boundaries | Completed | A | I | R | C | [7 empty] | A | I | I | R
| Businesses | Completed | A | I | R |  | C | [6 empty] | A | I | I | R
| Geography/Location | Completed | A | I | R | [8 empty] | A | I | I | R
| Specific Processes | Completed | A | I | R | [8 empty] | A | I | I | R
| Audience Inclusion | Completed | A | I | R | [8 empty] | A | I | I | R
| Audience Inclusion | Completed | A | I | R | [8 empty] | A | I | I | R
| Audience Inclusion | Completed | A | I | R | [8 empty] | A | I | I | R
| Audience Exclusion | Completed | A | I | R | [8 empty] | A | I | I | R
| Define our goals and objectives | Completed | A | I | R |  |  |  |  | D |  |  |  | A | I | I | R
| Define the impacts as a result of our goals | Completed | A | I | R | [5 empty] | D |  |  | A | I | I | R
| Define the Critical to Quality (CTC’s) and Key Metrics | Completed | A | I | R | [8 empty] | A | I | I |  |  |  | R
| Timeliness | Completed | A | I | R | [8 empty] | A | I | I |  |  |  | R
| Productivity | Completed | A | I | R | [8 empty] | A | I | I |  |  | R
| Adoption | Completed | A | I | R | [8 empty] | A | I | I | R
| Sustainability | Completed | A | I | R | [8 empty] | A | I | I | R
IDENTIFY
| Project Team | Completed | A | I | R | [8 empty] | A | I | I | R
| Stakeholders | Completed | A | I | R | [8 empty] | A | I | I | R
MAP
| Project review Plan | Completed | A | I | R | [8 empty] | A | I | I | R
| PRESENT EXECUTIVE SUMMARY | Completed | A | I | R | [8 empty] | A | I | I | R
REVIEW
| eLearning Content Review | Completed | A | I | [9 empty] | A | I | I | R
| Completion Rates Review | Completed | A | I | [9 empty] | A | I | I | R
| SURVEYS | [12 empty] | A | I | I | R
| Regional Manager Surveys | Completed | A | I | R | [8 empty] | A | I | I | R
| Survey New Hires that recently participated in the training program | Completed | A | I | R | [8 empty] | A | I | I | R
FINALIZE TOPICS
| Markets | Completed | A | I | R |  |  |  |  | C |  |  |  | A | I | I | R
| Products | Completed | A | I | R | [5 empty] | C |  |  | A | I | I | R
| Tools & Systems | Completed | A | I | R | [8 empty] | A | I | I | R
| Business Processes | Completed | A | I | R | [8 empty] | A | I | I | R
| Selling Skills | Completed | A | I | R | [8 empty] | A | I | I | R
| Ambassador Role | Completed | A | I | R | [8 empty] | A | I | I | R
| Certification Criteria | Completed | A | I | R | [8 empty] | A | I | I | R